ACCORD · OSUN STATE

ONE-PAGE EXECUTIVE BRIEF

Election Monitoring, Command & Vote Protection Platform

Budget Request: ₦38,000,000  |  Coverage: Osun State Only (30 LGAs · 332 Wards)

Purpose

Approve ₦38 million for statewide deployment of ACCORD’s digital election monitoring platform in Osun State — enabling real-time polling-unit visibility, evidence capture, controlled agent support (airtime/data), and election-day command coordination.

What Leadership Gets

• Live monitoring dashboard across all 30 LGAs and 332 wards

• Evidence archive (snapshots + recordings) for legal and strategic use

• Controlled airtime/data claims with anti-abuse rules and full audit trail

• Agent training, election-day command centre, and technical standby support

• Post-election operational report and evidence pack

Budget at a Glance

| Component | ₦ |
| --- | --- |
| Platform, branding & Osun catalog | 6,500,000 |
| Hosting, storage & security | 4,000,000 |
| Live streaming infrastructure | 3,500,000 |
| Agent airtime/data wallet (VTpass) | 8,000,000 |
| Training (30 LGAs) | 3,000,000 |
| Election-day command centre | 4,500,000 |
| Technical standby & field support | 3,500,000 |
| Devices & contingency kits | 2,000,000 |
| Project management & documentation | 1,500,000 |
| Contingency (~5%) | 1,500,000 |
| TOTAL | 38,000,000 |

Disbursement

40% on approval/kickoff (₦15.2m) · 35% on statewide activation (₦13.3m) · 25% on election-day readiness/final delivery (₦9.5m).

Decision Requested

Approve ₦38,000,000 for Osun-only implementation; nominate LGA focal persons; authorize phased disbursement; schedule leadership demo within 7 days.

Approval

Name: ___________________________    Title: ___________________________

Signature: ________________________    Date: ____________________________

Amount Approved: ₦38,000,000 (Osun State Only)