ACCORD

OSUN STATE

FORMAL PROPOSAL

Election Monitoring, Command

& Vote Protection Platform

Project Budget

₦38,000,000

(Thirty-Eight Million Naira Only)

Coverage: Osun State Only

30 Local Government Areas · 332 Wards · Statewide Polling Units

Presented to: ACCORD Leadership / Campaign Council

Prepared by: _______________________________

Date: _______________________________

Classification: Confidential

TABLE OF CONTENTS

1. Executive Summary

2. Strategic Context and Need

3. Scope of Work (Osun State Only)

4. Proposed Platform & Deliverables

5. Detailed Budget Breakdown — ₦38,000,000

6. Justification of Budget

7. Implementation Timeline

8. Governance, Security & Accountability

9. Key Performance Indicators

10. Disbursement Schedule

11. Decision Request

12. Conclusion

13. Signature and Approval Page

1. EXECUTIVE SUMMARY

This document presents a formal request for approval of ₦38,000,000 for the deployment, operation, and election-day management of a digital Election Monitoring, Command and Vote Protection Platform for ACCORD in Osun State only.

The platform will enable ACCORD to monitor polling units across all 30 LGAs in near real time; capture and store verifiable evidence (live feed, snapshots, and recordings); coordinate agents and LGA structures from a central command dashboard; disburse controlled airtime/data support with audit trails; escalate incidents rapidly with evidence-backed reporting; and produce post-election records for leadership and legal review.

2. STRATEGIC CONTEXT AND NEED

Election outcomes increasingly depend on speed, field visibility, and evidence quality. Without a structured digital system, field information arrives late, incidents are poorly documented, and leadership cannot act quickly enough across Osun’s 30 LGAs and 332 wards.

Common operational gaps this project addresses:

• Delayed or fragmented updates from polling units

• Inconsistent quality of field evidence

• Weak escalation structure for incidents

• Limited real-time visibility for senior leadership

• Inadequate post-election documentation for legal processes

• Uncontrolled or poorly audited field support spending

3. SCOPE OF WORK (OSUN STATE ONLY)

| Item | Coverage |
| --- | --- |
| State | Osun State only |
| Local Government Areas | 30 |
| Wards | 332 |
| Polling units | Statewide catalog support |
| Users | Agents, LGA coordinators, state command, admins |
| Duration | Pre-election setup + election period + post-election audit |

Out of scope: Other states. This budget is exclusively for Osun State operations.

4. PROPOSED PLATFORM & DELIVERABLES

A. Platform Layers

Agent Layer — polling-unit assignment, live reporting/stream, controlled airtime/data claims, claim history.

Administrative Layer — agent oversight, live unit status, evidence management, anti-abuse controls.

Command Layer — LGA/ward/state dashboards, incident escalation, leadership summaries, evidence-backed decisions.

B. Deliverables

1. Branded ACCORD–Osun monitoring web platform (agent, admin, command views)

2. Secure backend hosting, storage, and uptime support for election operations

3. Live feed and evidence capture (snapshots and recordings)

4. Controlled airtime/data claim system with admin limits and anti-abuse rules

5. Training for agents and coordinators across LGAs

6. Election-day technical command support

7. Post-election evidence packaging and operational report

5. DETAILED BUDGET BREAKDOWN — ₦38,000,000

| S/N | Budget Line | Amount (₦) | Purpose |
| --- | --- | --- | --- |
| 1 | Platform development, customization & Osun branding | 6,500,000 | ACCORD/Osun adaptation, catalog, dashboards, admin controls |
| 2 | Cloud/server hosting, storage, backups & security | 4,000,000 | API hosting, recordings storage, SSL, hardening, uptime |
| 3 | Live streaming infrastructure (WebRTC capacity) | 3,500,000 | Concurrent statewide live feeds on election day |
| 4 | Field agent support wallet (airtime/data) | 8,000,000 | Controlled VTpass claims so agents stay online |
| 5 | Agent & coordinator training (30 LGAs) | 3,000,000 | Onboarding, SOPs, simulation drills, materials |
| 6 | Election-day command centre operations | 4,500,000 | Situation room, monitors, connectivity, logistics |
| 7 | Technical standby & field support team | 3,500,000 | Engineers/support officers for critical window |
| 8 | Devices & contingency kits (selected LGA leads) | 2,000,000 | Power banks, backup data, critical field kits |
| 9 | Project management, documentation & compliance | 1,500,000 | Reporting, oversight, documentation |
| 10 | Contingency (approx. 5%) | 1,500,000 | Unforeseen election-day operational needs |
|  | TOTAL | 38,000,000 |  |

6. JUSTIFICATION OF BUDGET

₦38 million is calibrated to Osun’s statewide scale and election-day peak demand. Major cost drivers are live-stream capacity, secure evidence storage, agent connectivity support, LGA-wide training, and command-centre operations. This budget balances technology, field operations, and election-day response — not software alone.

7. IMPLEMENTATION TIMELINE

| Phase | Period | Activity |
| --- | --- | --- |
| 1 | Week 1–2 | Leadership approval, hosting setup, admin configuration, branding |
| 2 | Week 3–4 | Agent onboarding & LGA training; pilot in selected LGAs |
| 3 | Week 5–6 | Full Osun rollout; readiness drills; wallet funding |
| 4 | Election window | Live command operations, evidence capture, escalation |
| 5 | Post-election | Audit pack, recordings archive, final leadership report |

8. GOVERNANCE, SECURITY & ACCOUNTABILITY

• Role-based access controls for leadership, admins, and agents

• Approved airtime/data denominations only, with optional one-phone-one-claim rules

• Full claim and evidence audit logs

• Secure hosting, encrypted transport, and controlled media retention

• Weekly financial/operational reporting to ACCORD leadership

• Post-project expenditure and performance report

9. KEY PERFORMANCE INDICATORS

• Percentage of assigned polling units actively reporting

• Live monitoring uptime by ward and LGA

• Incident escalation response time

• Volume and quality of validated evidence entries

• Airtime/data claim compliance rate

• Legal evidence readiness score post-election

10. DISBURSEMENT SCHEDULE

| Tranche | % | Amount (₦) | Trigger |
| --- | --- | --- | --- |
| 1 | 40% | 15,200,000 | Contract/approval + kickoff |
| 2 | 35% | 13,300,000 | Training complete + statewide activation |
| 3 | 25% | 9,500,000 | Election-day readiness confirmed / final delivery |
|  | 100% | 38,000,000 |  |

11. DECISION REQUEST

ACCORD leadership is respectfully requested to:

1. Approve the Osun-only project budget of ₦38,000,000

2. Authorize phased disbursement against milestones

3. Nominate state/LGA focal persons for onboarding

4. Direct pilot and statewide adoption by field teams

5. Schedule leadership demonstration within 7 days of approval

12. CONCLUSION

This ₦38 million proposal is a focused investment in ACCORD’s Osun State vote-protection and election command capacity. It provides the technology, training, field support, and election-day operations required to monitor polling activity statewide with discipline, speed, and evidence integrity.

With approval, implementation can commence immediately under a phased, measurable, and accountable model aligned with ACCORD leadership priorities.

13. SIGNATURE AND APPROVAL PAGE

Document Title:

ACCORD Osun State — Election Monitoring, Command & Vote Protection Platform (Formal Proposal)

Project Budget: ₦38,000,000 (Thirty-Eight Million Naira Only)

Coverage: Osun State Only

Prepared By

Name: _______________________________________________

Title/Unit: ___________________________________________

Signature: ____________________________________________

Date: ________________________________________________

Reviewed By

Name: _______________________________________________

Title: ________________________________________________

Signature: ____________________________________________

Date: ________________________________________________

Approved By

ACCORD Leadership / Authorized Signatory

Name: _______________________________________________

Title: ________________________________________________

Signature: ____________________________________________

Date: ________________________________________________

Amount Approved

₦38,000,000 (Osun State Only)

Official Stamp / Seal: _______________________________